| Project Name and Information | Proyecto Indigo Azul (Phase 3) Proyecto Indigo Azul (Blue Indigo Project) is a demonstration Food Forest and learning center for youth and young adults. It is currently in its 3rd season of growth and development of the Food Forest. The project is located at Azucena 1112, Paso De Guayabo,Paso Ancho 48373 Puerto Vallarta,MX. Proyecto Indigo Azul was created by a group of volunteers from Seattle,WA USA and Mexico City,MX. This location will serve as the blueprint to teach life skills to youth and young adults in urban and rural areas. |  |  |
| --- | --- | --- | --- |
| Project Manager | Ivette Milo | Sponsors | Humanitarian Social Innovations https://hsifiscalsponsor.org/ Jeremy Bowers Culture Shock Program www.nwkids.org |
| Project ID: | 22 | Date Prepared: | 06/25/2024 |

Project Overview:

| Project Purpose: | The purpose of this project is to build a long term demonstration center where students can come and receive life skill training centered around the 4 essential human needs of food, water, energy and shelter. Our systems use methods that are simple enough to be carried out by those with no prior agricultural or technical experience.Second language acquisition classes also will be provided free of charge to selected students to increase cultural awareness and communication skills. |
| --- | --- |
| Project Description | - Desired Outcomes - Production of nutritious produce - Environmental awareness - Responsibility & Inclusiveness - Cultural exchange - Second language acquisition - Artistic expression - Life Skills A hands on learning center where kids and young adults can come for free to study life skills surrounding the basic needs of food,water,energy and shelter, Over 250+ Varieties of Heirloom fruits and vegetables,trees, herbs and flowers have been planted to date on the property.Our food systems are working well and and our methods have proven to be effective and easily accessible to all. New methods of growing plants without soil are being studied and tested. |
| High Level Requirements | Professional Hires will be required in order to ensure professionalism and consistency . 1. Project Management & Development 2. Accounting 3. Fundraising 4.On site staff |
| High Level Risks | - Failure to gain effective and measurable government support - Failure to get the public school systems to honestly acknowledge and consider if this style of education can be integrated into the school systems to provide greater possibilities for human potential. - Failure to secure the proper sponsors ,donations and community support needed to carry the project into its self sustainable stages. (Year 5-6 ) - Failure as a collective to provide effective teachings for the next generations of the world to have the life skills to be self reliant. - Failure to properly demonstrate that our methods can be used by everyday people anywhere in both rural and urban areas using easily accessible recycled and low cost materials. - Failure to come to an agreement on purchase of the property by 2030 |
| Preliminary Budget: | We are seeking to raise $10,000 usd / $181,500 mxn to complete Phase 3 |

Project Objectives: List each project objective in measurable terms and the agreed upon success criteria.

| Objective | Success Criteria |
| --- | --- |
| Fundraising Construction Food Forest Fiscal Sponsor Unpaid Staff Paid Staff. (Hire # 1) | 10k Fundraiser Goal successful The Following Construction should be complete by September 1st/2024. Perimeter Property Fence completed, Main Roof (Front/Back) Greenhouses completed (upper/ lower) Workshop area(Upper) Bathroom(Main House) Bathroom( Exterior ) Mud room (Main House) Aqua Culture pond repair (Front yard) 200 + Varieties of plants, fruits,flowers, vines, trees, herbs and heirloom vegetables to be planted ,propagated and studied. 10% 5 Volunteers committed to 1 day a week Project Development (Veronika Dimitrova) |
| Schedule Objective | Oct 1st 2024 All construction |
| Cost Objective | 5500 Construction 3000 Project Development 1000 Fiscal Sponsor |
| Potential Reserve Budget | 9000 MXN /500 USD |
| Any other funds remaining after cost objectives are completed will be rolled back into the reserve budget |  |

Milestone Schedule: List key milestones in chronological order with associated target achievement dates.

| Page 4 of 4 Milestone Schedule |  |
| --- | --- |
| Milestone Name | Due Date |
| Project Start Season 1 09/2021 | 09/2022 Beginning stages of soil restoration and plant identification completed. 100 purpose specific trees planted. Legal Formation of nwkids.org. Volunteer donations and labor to begin working . Community involvement and interaction. Positive networking between USA and Mexico |
| Season 2 09/2022 | 09/2023 1 year of growth. Fruit trees, bananas, bamboo are established. Mango Harvest over 250lbs |
| Season 3 09/2023 | 09/2024 2 years of growth on property, Bamboo patch doubled in size .Main house is half finished remodeling and is ready for kitchen and bathroom work. New growing systems are in place . Over 250 new varieties of heirloom seeds have been sourced and planted. Commercial propagation of plants and trees begins. Fundraising will be initiated.. On schedule for checkpoint and evaluation 09/01/24 |
| Project Checkpoint and Evaluation | 09/01/2024 checkpoint before moving forward with the next 2 year plan. Board meeting where progress and budget will be reevaluated along with procedures, staff and best processes. Holiday Fundraising strategies can be discussed |
| Project Completion | 2030 Land Purchased & Project Self Sustained |

Project Stakeholder List: Provide the names of key or primary stakeholders and their project roles.

| Project Stakeholder List |  |
| --- | --- |
| Stakeholder Name | Project Role |
| Ivette Milo | Project Manager & Volunteer Proyecto Indigo Azul (Mexico) |
| Jeremy Bowers | Co-Creator of the Culture Shock program ( USA) |
| Aleksa Cegar | Culture Shock Representative (Serbia) |
| Humanitarian Social Services (HSI) | Fiscal Sponsor (USA) |
| Community Of Paso De Guayabo and culture shock students | Local Community (Mexico) Students of the Culture Shock Program (USA,MX,SERBIA) |

Project Manager Authority: This document establishes the project manager authority as follows:

| Staffing Decisions | The project manager has the authority to make decisions about all staffing related issues |
| --- | --- |
| Technical Decisions | Technical decisions will be first discussed in an open group of all stakeholders to seek feedback. and seek out the most qualified person in that area of expertise. Group input is welcomed and used in order to reach the best solution. The project manager is granted the authority to make the final decisions. |
| Budget | $10,000 USD / $181,500 mxn |
| Other: <specify> | Project manager is granted the authority to set up brand protection , content creation ,trademarking and any other legal transactions under the name “Proyecto Indigo Azul” or “Indigo Azul” |

This Project Charter is approved and authorized in accordance with project management governance.

| Approvals: |  |  |  |
| --- | --- | --- | --- |
| Project Manager Name: | Ivette Milo | Project Manager Signature | Ivette Milo |
| Sponsor Name: | Jeremy Bowers | Sponsor Signature: | Jeremy Bowers |
| Date: | 06/26/2024 | Date: | 06/26/2024 |